## Project 1
Software Feature Checklist and Bug Report
Title | Done? | Project Component | Project Category | Developer | Date Start | Completion Date | Priority | Details | Completion Notes
Edge Scrolling Does not function properly in full build |  | UI | Bug | None |  |  | Low | Edge Scrolling currently only functions properly in the display port window in the editor, Pressing "Launch Game" causes it to list the camera downward with no change based on cursor location
Build Button Should Display Sub-Menu / Buttons |  | UI | Feature | None |  |  | High | Feature Request for Build Button to only be displayed when a builder is selected, additionally, upon press the build button should expand into an intuitve menu of available structures
Complete Seige Weight Paint + Rigging |  | Mesh | Other | None |  |  | Medium | Complete Armature Rigging and weight painting for Siege Minion Mesh (Does not include Animation Set)
Adjust Scaling on Mine Static Mesh |  | Mesh | Refactor | None |  |  | High | Static mesh + Collision Mesh is ~100x smaller than intended size. This should be edited in either the blender file or the import option into UE4
RTS Camera Zoom Limits Do Not Match Implementation |  | Object | Refactor | None |  |  | Low | The Camera (at least as of now), currently sits below the threshold for forward zoom, making it impossible to zoom in before zooming out substatially
Create Spawner Static Mesh |  | Mesh | Feature | None |  |  | High | Generate the Initial design of the Spawner mesh (includes collision)
Create Mine Thumbnail |  | Mesh | Other | None |  |  | Medium | Blender Features the ability to create thumbnails that will be used as the button selection from the build sub-menu. As a test case, please generate this for the mine structure.
|  | Other | None | None |  |  | N/A
|  | Other | None | None |  |  | N/A
|  | Other | None | None |  |  | N/A
|  | Other | None | None |  |  | N/A
|  | Other | None | None |  |  | N/A
|  | Other | None | None |  |  | N/A
|  | Other | None | None |  |  | N/A
|  | Other | None | None |  |  | N/A
|  | Other | None | None |  |  | N/A
|  | Other | None | None |  |  | N/A
|  | Other | None | None |  |  | N/A
|  | Other | None | None |  |  | N/A
|  | Other | None | None |  |  | N/A

## TableData
Developer | Category | Severity | Component
None | Feature | Low | UI
Stephen S. | Bug | Medium | Mesh
Peter P. | Refactor | High | Object
Matt A. | Other | Very High | Other
Chris E. | None | N/A